## Project Timeline
TEMPLATE PROJECT TIMELINE
Gantt Chart untuk Perencanaan dan Tracking Proyek
Nama Project | SEO Marketing Plan |  |  |  | Isi kolom merah muda: fase/aktivitas, PIC, status, tanggal mulai, tanggal selesai, dan progress. Bar di kanan akan mengikuti tanggal otomatis.
Project Manager | Nama PIC
Tanggal Mulai Timeline | 2026-01-05
Tanggal Selesai Otomatis | 2026-07-31
No. | Tipe | Fase / Aktivitas | PIC | Status | Mulai | Selesai | Progress | 2026-01-05 | 2026-01-12 | 2026-01-19 | 2026-01-26 | 2026-02-02 | 2026-02-09 | 2026-02-16 | 2026-02-23 | 2026-03-02 | 2026-03-09 | 2026-03-16 | 2026-03-23 | 2026-03-30 | 2026-04-06 | 2026-04-13 | 2026-04-20 | 2026-04-27 | 2026-05-04 | 2026-05-11 | 2026-05-18 | 2026-05-25 | 2026-06-01 | 2026-06-08 | 2026-06-15 | 2026-06-22 | 2026-06-29
1 | Fase | Foundational | Marketing | In Progress | 2026-01-05 | 2026-04-24 | 45%
| Task | Keyword research | SEO | Done | 2026-01-05 | 2026-02-13 | 100%
| Task | Analytics setup | SEO | In Progress | 2026-02-09 | 2026-03-13 | 60%
2 | Fase | Semantic Core | Marketing | Not Started | 2026-03-02 | 2026-06-26 | 20%
| Task | General semantic mapping | SEO | Not Started | 2026-03-02 | 2026-03-27 | 0%
| Task | Landing page mapping | Content | Not Started | 2026-04-06 | 2026-05-15 | 0%
| Task | Content landing brief | Content | Not Started | 2026-05-18 | 2026-06-26 | 0%
3 | Fase | Onsite Optimization | Marketing | In Progress | 2026-01-05 | 2026-06-12 | 35%
| Task | Titles, metas, H1 | SEO | Done | 2026-01-05 | 2026-01-23 | 100%
| Task | Additional content descriptions | Content | In Progress | 2026-01-26 | 2026-03-06 | 45%
4 | Fase | Technical | Web | In Progress | 2026-02-09 | 2026-06-12 | 30%
| Task | Competitor analysis | SEO | In Progress | 2026-02-09 | 2026-03-20 | 50%
| Task | Duplicate page cleaning | Web | Not Started | 2026-04-06 | 2026-05-15 | 0%
| Task | Robots.txt review | Web | Not Started | 2026-05-18 | 2026-06-12 | 0%
5 | Fase | Reporting & Launch | Marketing | Not Started | 2026-06-15 | 2026-07-31 | 0%
| Task | Weekly performance report | SEO | Not Started | 2026-06-15 | 2026-07-10 | 0%
| Task | Final launch review | Marketing | Not Started | 2026-07-13 | 2026-07-31 | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
| Task |  |  | Not Started |  |  | 0%
LEGENDA
Fase
Task
Done
Minggu berjalan
Input manual
Rumus/otomatis

## Petunjuk
PETUNJUK TEMPLATE PROJECT TIMELINE
1 | Isi Nama Project, Project Manager, dan Tanggal Mulai Timeline pada bagian atas sheet Project Timeline.
2 | Ubah kolom Fase / Aktivitas, PIC, Status, Mulai, Selesai, dan Progress sesuai proyek.
3 | Gunakan Tipe = Fase untuk bar fase besar dan Tipe = Task untuk aktivitas detail.
4 | Bar timeline di kanan akan otomatis berwarna sesuai tanggal mulai dan selesai.
5 | Tambahkan aktivitas baru di baris kosong yang sudah tersedia sampai baris 38.